## Sheet1
Number | Phase | Activities | Start Date | Finish Date | Duration (days) | Status
1 | Initiation and Planning | This phase sets the foundation for the BI project by researching Golden Gate’s business landscape, defining objectives, and establishing the project scope. Key activities include industry analysis, identifying business challenges, cost estimation, and forming the project team. The project charter and development lifecycle are also finalized to ensure a clear roadmap. | 2025-03-01 | 16/01/2025 | 10 | Completed
2 | Requirement Analysis | This phase focuses on gathering and defining business and technical requirements through stakeholder interviews, process analysis, and KPI identification. It ensures that all project requirements are well-documented, reviewed, and approved to align with business needs before moving forward. | 17/01/2025 | 27/01/2025 | 7 | Completed
3 | Data Preparation and Modeling | In this phase, raw data is collected, cleaned, and transformed into structured formats for analysis. Data models, including schemas, relationships, and key metrics, are developed and validated to ensure accuracy and consistency with business requirements. | 20/01/2025 | 28/01/2025 | 7 | Completed
4 | Data Integration | This phase involves extracting data from various sources, transforming it for consistency, and loading it into the BI system. ETL processes are designed and tested to ensure seamless data flow, accuracy, and automation for continuous updates. | 28/01/2025 | 2025-05-02 | 7 | Completed
5 | Development of Sales Module | The Sales Module is built to provide insights into sales performance, trends, and regional or product-specific analysis. Dashboards and reports are developed to help decision-makers track and optimize sales strategies. | 2025-06-02 | 2025-12-02 | 5 | Completed
6 | Development of Marketing Module | This phase focuses on building BI tools for marketing analytics, including campaign performance tracking, customer segmentation, and feedback analysis. The module enables data-driven marketing decisions and performance optimization. | 13/02/2025 | 19/02/2025 | 5 | Completed
7 | Testing and Quality Assurance | Before deployment, rigorous testing is conducted, including unit testing, system integration testing, and user acceptance testing (UAT). This ensures the system meets functional, performance, and data accuracy standards. | 20/02/2025 | 26/02/2025 | 5 | Completed
8 | Deployment and Training | The BI system is deployed to the production environment, and training sessions are conducted for end-users. User manuals and guides are provided to ensure smooth adoption, and initial support is offered during the transition phase. | 27/02/2025 | 2025-05-03 | 5 | Completed
9 | Post Implementation Review | This phase evaluates the project's success, gathers lessons learned, and identifies areas for improvement. A maintenance team is established to address any post-deployment issues and ensure system sustainability. | 2025-06-03 | 2025-07-03 | 2 | Completed
10 | BI Solution Report Completion | A final report documenting the entire project, key findings, and outcomes is compiled. The report includes visual data representations, insights, and recommendations, serving as a reference for future BI initiatives. | 2025-10-03 | 2025-11-03 |  | Completed
BI PROJECT CLOSURE AND COMPLETE