## Sheet1
No | Action | Owner | Due Date
1 | Conduct project kickoff meetings with stakeholders, define scope, objectives, and expected outcomes. Finalize the project team and assign responsibilities. | Project Manager | 2025-03-01
2 | Perform business landscape research on Golden Gate's market, analyze competitors, and document key challenges in the restaurant industry. | Business Analyst | 2025-05-01
3 | Estimate project costs, identify resource requirements, and finalize the project budget. Develop and approve the project charter. Send the Initiation Phase report progress to the Project Sponsor. | Project Manager | 16/01/2025
4 | Conduct stakeholder interviews to gather business requirements, identify key performance metrics, and document technical needs for BI implementation. | Business Analyst | 16/01/2025
5 | Document and finalize business and technical requirements. Review and obtain approvals from stakeholders before moving forward. Send the report progress to the Project Sponsor. | Business Analyst | 19/01/2025
6 | Collect raw sales and marketing data, perform data cleaning, and prepare structured datasets for modeling. | Data Analyst & Engineer | 20/01/2025
7 | Develop logical data models, define schema relationships, and ensure alignment with business needs. Validate data accuracy and consistency. | Data Analyst & Engineer | 27/01/2025
8 | Implement and test ETL (Extract, Transform, Load) processes to automate data integration and ensure seamless data flow from multiple sources. | Data Analyst & Engineer | 30/01/2025
9 | Develop the Sales Module, including dashboards for sales trends, product performance, and regional sales analysis. Conduct initial testing. Send the report progress to the Project Sponsor. | Product Developer | 2025-11-02
10 | Transition from manual data extraction to API-Based Real-Time Integration. | Product Developer | 16/02/2025
11 | Develop the Marketing Module, including customer segmentation analysis, campaign performance tracking, and predictive analytics. Send the report progress to the Project Sponsor. | Product Developer | 17/02/2025
12 | Conduct unit testing and system integration testing to validate data accuracy, BI tool performance, and dashboard functionality. | QA/QC | 17/02/2025
13 | Approval change from Project Sponsor | Project Sponsor | 18/02/2025
14 | Organize User Acceptance Testing (UAT) with marketing and sales teams to gather feedback, ensure usability, and address potential system gaps. | QA/QC & Business Analyst | 21/02/2025
15 | Deploy the BI system to the production environment and ensure all necessary configurations are in place. | Project Manager | 25/02/2025
16 | Conduct user training sessions on dashboard usage, report generation, and system functionalities. Provide documentation and guidelines. | Business Analyst | 27/02/2025
17 | Perform a post-implementation review, collect feedback from stakeholders, and identify areas for future improvement. | Entire Project Team | 2025-07-03
18 | Finalize and submit the BI solution report, including key insights, data visualizations, lessons learned and recommendations for future BI development. | Entire Project Team | 2025-11-03
PROJECT DIARY