## Risk LOG
RISK LOG
No. | Risk | Description | Severity | Probabilty of Occurrence | Contingency and Mitigation Actions (incl. "Plan B")
1 | Changing customer requirements | Delays due to constant changes in requirements. | Low | High | 1. Require the customer to clearly define the requirements up front with an SRS (Software Requirement Specification) document. 2. Limit the number of free changes, then charge for additional changes.
2 | BI system mismatch | BI reports and insights may not align with business needs, affecting decision-making. | Very High | Medium | 1. Conduct thorough research before implementation to ensure BI meets actual needs. 2. Continuously gather feedback from departments to adjust the system accordingly. 3. Run pilot tests before full deployment.
3 | Extra requirement costs | Unexpected costs may cause budget overruns, delaying implementation. | Low | High | 1. Define the project scope from the start and sign a tight contract. 2. Budget for contingencies (~10-20% of total budget).
4 | Data format inconsistency | Inaccurate data input may result in unreliable BI reports. | High | High | 1. Standardize data input and processing workflows across different systems. 2. Use ETL tools for automated data conversion. 3. Establish common data standards across integrated systems.
5 | Human data errors | Data errors may lead to incorrect analysis and decision-making. | Medium | High | 1. Use Data Validation Checks to alert you when data is formatted incorrectly. 2. Automate data entry with API integration.
6 | Poor task prioritization | Mismanagement of tasks may slow down the project timeline. | High | Medium | 1. Use project management frameworks like Kanban or Scrum to prioritize tasks. 2. Develop a task prioritization matrix based on impact and urgency. 3. Regularly review progress and adjust priorities as needed.
7 | Deployment technical errors | System malfunctions may hinder operational efficiency. | Very High | Medium | 1. Run tests on a staging environment before deploying to the real world. 2. Create a rollback plan to have a backup plan in case of errors.
8 | Limited resources | Lack of resources may prolong project delivery. | Very High | Medium | 1. Plan detailed resource allocation and distribute workload efficiently. 2. Leverage automation tools to reduce labor demands. 3. Propose a contingency budget to handle financial constraints.
9 | Employee resistance | Employee hesitation in using the system may slow down adoption. | Medium | High | 1. Explain the benefits of the BI system by demonstrating performance & efficiency. 2. Organize training & support sessions to help employees get familiar with the new system.
10 | Inadequate training | Untrained staff may struggle with system functionality, reducing efficiency. | Very High | Low | 1. Develop comprehensive training materials and conduct regular training sessions. 2. Provide online learning modules or 24/7 support for easy access. 3. Assess employees' learning progress and adjust training programs accordingly.