## Sheet1
Project Overall Budget | 2025 | [8 empty] | Plan | % Completed | EV
Category | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Software and Licensing | 2025 Week 1: 100000 | 100000 | 100% | 100000
Consulting Services | 2025 Week 1: 2000; 2025 Week 2: 2000 | 4000 | 100% | 4000
Cloud Infrastructure (AWS) | 2025 Week 1: 5000 | 5000 | 100% | 5000
Networking Equipment (Firewalls, Switches, Routers) | 2025 Week 1: 11200 | 11200 | 100% | 11200
Evaluate and collect requirements | 2025 Week 3: 1100 | 1100 | 100% | 1100
Analyze Data | 2025 Week 4: 2500; 2025 Week 5: 2500 | 5000 | 100% | 5000
Data Integration/ETL (Data Consolidation & Transformation) | 2025 Week 5: 12250; 2025 Week 6: 12250 | 24500 | 100% | 24500
Visualization | 2025 Week 6: 2500; 2025 Week 7: 2500; 2025 Week 8: 2500 | 7500 | 100% | 7500
Implementation | 2025 Week 6: 5000; 2025 Week 7: 5000; 2025 Week 8: 5000 | 15000 | 100% | 15000
Testing | 2025 Week 8: 6000 | 6000 | 100% | 6000
User Training | 2025 Week 8: 2250; 2025 Week 9: 2250 | 4500 | 100% | 4500
Maintenance and Support | 2025 Week 9: 1400 | 1400 | 100% | 1400
Salary (Labor) | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 |  | 2400 | 100% | 2400
Weekly PV | 118500 | 2300 | 1400 | 2800 | 15050 | 20050 | 7800 | 16050 | 3650 | 187600 | 100% | 187600
PV or cumulative plan | 118500 | 120800 | 122200 | 125000 | 140050 | 160100 | 167900 | 183950 | 187600
Weekly AC | 120950 | 1400 | 5300 | 24725 | 3925 | 4000 | 6075 | 5975 | 15250
AC or cumulative actual | 120950 | 122350 | 127650 | 152375 | 156300 | 160300 | 166375 | 172350 | 187600
Weekly EV | 118500 | 2300 | 1400 | 2800 | 15050 | 20050 | 7800 | 16050 | 3650
EV or cumulative actual | 118500 | 120800 | 122200 | 125000 | 140050 | 160100 | 167900 | 183950 | 187600
CV = EV - AC | -2450 | -1550 | -5450 | -27375 | -16250 | -200 | 1525 | 11600 | 0
SV = EV - PV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPI = EV/AC | 97.97% | 98.73% | 95.73% | 82.03% | 89.6% | 99.88% | 100.9% | 106.7% | 100%
SVI = EV/PV | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Budget (Overall Project/Program)