## Business Case
Project Information
Project Name | Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules. |  | Group | 4
Project Description | A Business Intelligence (BI) system for Golden Gate Restaurant Chain designed to centralize data, gain customer insights, optimize operations, enhance marketing effectiveness, and ensure scalability for long-term growth and adaptability.
Project Sponsor | Assoc. Prof. Ho Trung Thanh, Ph.D.
Program Manager | Assoc. Prof. Ho Trung Thanh, Ph.D.
Project Manager | To Nguyen Tuong Vy
Organization(s) | Golden Gate Restaurant Chain
Target Start Date | 3rd January, 2025 | Target End Date: | 11th March, 2025
Five forces of F&B industry
Threat of new entrants | Medium - High | Reason: The F&B industry in Vietnam has low entry barriers, enabling small restaurants and startups to enter easily by leveraging technology and online business models. Challenges for new entrants: Supply chain management, scaling operations, and technology investments. Golden Gate’s Advantage: Nearly 400 restaurants and 22 brands create significant entry barriers for new competitors. Potential Risks: Competitors may focus on niche markets or introduce competitively priced products/services. Recommended Strategy: Golden Gate should continue innovating, enhancing customer experience, and integrating technology to maintain its competitive edge.
Bargaining power of buyers | High | Factors: Consumers prioritize food quality, service, and ambiance, with abundant options and reliance on social media reviews influencing decisions. Price sensitivity is high in mid-range segments. Risks: Negative reviews, frequent shifts in dining preferences, and rising competition make customer retention challenging. Strategy: Enhance service quality, implement personalized loyalty programs, monitor online feedback, and align promotions with customer needs.
Bargaining power of suppliers | Low - Medium | Advantage: Golden Gate’s scale (500+ restaurants) ensures stable, large orders, reducing supplier power for common ingredients. Risks: Limited suppliers for premium imports (e.g., American beef, wine) increase dependency and vulnerability to currency fluctuations and global events. Strategy: Establish long-term partnerships with suppliers, diversify sources, and prioritize local sourcing where feasible.
Threat of substitute products or services | High | Challenges: Online food delivery services (e.g., GrabFood, ShopeeFood) and alternative models (e.g., street food, food trucks) attract customers with convenience and lower costs, reducing dine-in demand. Market Dynamics: Vietnam’s food delivery market reached $587M in 2020 and is expected to hit $2.7B by 2025, with 83% of consumers using delivery services. Strategy: Expand delivery options, enhance on-site experiences, and diversify offerings to remain competitive.
Competitive Rivalry | High | The F&B industry in Vietnam is highly competitive, with over 304,700 establishments as of June 2024, despite a 3.9% decline from 2023. Major players like Redsun ITI (ThaiExpress, King BBQ, Hotpot Story) intensify competition, especially in buffet, grilling, and hotpot models. Golden Gate’s Position: Maintains leadership with a wide network and diverse brand portfolio but faces direct pressure from rivals. Strategy: Focus on brand differentiation, menu innovation, and maintaining strong customer loyalty.
Project Details
Problems | Inconsistent Data Management: Multiple brands use different systems and data formats (CSV, Excel, SQL), leading to manual, error-prone data aggregation and difficulty in generating comprehensive reports. Fragmented Customer Insights: Customer data is scattered across various systems, limiting the ability to analyze behavior and personalize experiences effectively. Operational and Cost Management: Difficulty tracking KPIs, managing inventory, and forecasting demand, leading to inefficiencies, shortages, or surpluses. Marketing Effectiveness: Measuring the true ROI of campaigns is challenging due to external factors and difficulty isolating promotion-driven sales increases.
Contribution to Business Solution | Centralized Data management: The system consolidates Data from multiple sources, including CRM, POS, inventory, and financial systems, into a unified platform. This centralization ensures seamless access to reliable Data, empowering leadership to make informed, Data-driven decisions. Operational Excellence: by streamlining operations such as inventory management, demand forecasting, and Supply chain optimization, The system reduces inefficiencies. Enhance Customer Experience: The system provides insights into Customer behavior and preferences, enabling highly targeted marketing campaigns. Personalized offers and loyalty programs tailored to customer needs foster long-term relationships and improve retention rates. Support for Digital Transformation: Modernizing outdated systems and integrating them with advanced BI tools helps The company embrace The Digital age. This Transformation positions Golden Gate as a tech-savvy leader, capable of adapting to shifting market dynamics.
Options Considered | Option 1: Maintain Current Systems (Status Quo) Option 2: Partial Upgrades to Existing Systems Option 3: Build a Centralized BI System (Chosen Option)
Benefits | Sales Performance Optimization - Improved Sales Reporting Accuracy: By integrating sales data from POS systems into the BI platform, the company can reduce reporting errors by 20%, ensuring more accurate daily and monthly performance tracking. - Revenue Growth through Forecasting: Enhanced sales forecasting with BI tools will increase forecasting accuracy by 15%, helping restaurants anticipate demand better and reduce lost sales during peak periods, potentially boosting revenue by 1-2%. Marketing Campaign Effectiveness - Increased Campaign ROI: BI-driven customer segmentation will enable personalized marketing campaigns, improving the return on investment (ROI) for promotions by 10%. - Targeted Upselling: Insights from the BI system can guide targeted upselling strategies, such as recommending high-margin items based on customer preferences, potentially increasing average transaction value by 5%. Improved Decision-Making on Sales and Marketing - Real-Time Analytics: Dashboards will provide real-time data on campaign performance and sales trends, reducing decision-making time by 20%. - Quick Adaptation to Market Trends: With actionable insights, the marketing team can respond to evolving customer preferences (e.g., healthier options or delivery services), reducing the time to adjust strategies by 25%. Customer Retention and Loyalty - Loyalty Program Optimization: Better insights into customer behavior will increase active loyalty program participation by 10%, strengthening the brand’s relationship with its existing customer base. - Higher Retention Rates: Personalized marketing through the BI system is expected to improve customer retention rates by 5%. Competitive Advantage: - Leveraging BI tools helps close the gap with competitors that already use AI and advanced analytics. - Enables the company to stay ahead by adapting quickly to emerging trends and customer preferences. Scalability and Adaptability - A centralized system ensures consistency in service quality and operational standards across locations, even as the business expands. - The system’s modular design accommodates future updates to meet evolving market demands and regulatory changes.
Timescales | Initial analysis shows that the project will take approximately 10 weeks to implement
Costs | Fixed Cost Related to Project Software and Licensing BI Tools (Power BI) – Enterprise licenses for centralized BI reporting: $0 ETL Tool Licensing (Visual Studio 2022) – Data pipeline automation: $20,000 Database License (SQL Server on-premises) – Formatting data: $80,000 Evaluate and Collect Requirements Surveys & Questionnaires – Distributing forms to staff and management: $250 Process Documentation – Mapping workflows, identifying data sources, and defining BI integration: $300 Requirement Validation – Reviewing data with stakeholders and refining requirements: $250 Competitive Benchmarking – Analyzing competitors’ BI solutions: $300 Data Integration/ETL (Data Consolidation & Transformation) Custom Development for ETL Pipelines – Integrating POS, customer insights, and operational analytics: $7,000 API & Connector Development – Connecting BI dashboards with internal systems (CRM, ERP, etc.): $15,000 Data Cleaning & Quality Management – Rectifying inconsistencies in collected data: $2,500 Analyze Data Descriptive Analytics – Summary reports on sales, inventory, and performance: $1,500 Predictive Analytics – Forecasting trends and optimizing operations: $2,000 Customer Insights Analysis – Analyzing customer behavior and marketing strategies: $1,500 Visualization Dashboard Development – Creating interactive BI dashboards: $5,000 Report Customization – Customizing reports for different stakeholders: $2,500 Salary (Labor) Project Manager (1 person): $600 Data Analysts & Engineers (1 person): $400 QA/QC Specialist (1 person): $400 Product Developer (1 person): $500 Business Analyst (1 person): $500 Consulting Services BI Consulting Fees (External Experts) – BI consultant, customization support, and declarative development: $4,000 User Training Training Sessions for Employees (120 employees) – Online or in-person training: $3,000 Training Materials (Documentation, Videos, Guides) – Content creation and distribution: $1,500 Testing Functional Testing – Ensuring correct BI dashboard operations: $1,500 Performance Testing – Query speed and load handling: $1,500 Security & Compliance Testing – Ensuring data security and compliance: $1,500 User Acceptance Testing (UAT) – End-user testing before deployment: $1,500 Implementation Cost Internet & Network Expenses – Dedicated broadband connections for 20 locations: $1,800 Electricity & Power Costs – Increased power usage for BI infrastructure: $2,200 Office Setup & Operational Costs – Temporary workspace for the BI deployment team: $11,000 Maintenance and Support System Updates & Patches – Bug fixes, version upgrades, and troubleshooting: $1,000 Backup & Disaster Recovery – Cloud-based or on-prem backup solutions: $400 Cloud Infrastructure (AWS) Cloud Storage – Storing transaction data, customer records, and analytics: $1,000 BI Servers & Compute Instances – Running BI analytics and data visualization: $4,000 Networking Equipment (Firewalls, Switches, Routers) Enterprise-Grade Firewalls – Securing data transmission: $10,000 Redundant VPN Setup for Secure Remote Access – Secure tunneling for executives and analysts: $1,200 Total Estimated Cost: $187,600
Risks | Technical Risks - System Integration Issues: Difficulty in integrating legacy systems with the new BI platform may cause delays or functionality gaps. - Data Quality Problems: Inconsistent or incomplete data could affect the accuracy of analytics. Project Management Risks - Scope Creep: Additional requirements or changes during the project may lead to budget and timeline strain. - Timeline Delays: Dependencies on external vendors or consultants could cause delays in implementation. Financial Risks - Budget Overruns: Unexpected costs may exceed the allocated budget. - ROI Realization Risk: The BI system might take longer than expected to deliver measurable benefits. User Adoption Risks - Resistance to Change: Employees may resist adopting the new system. - Skill Gaps: Users may lack the necessary skills to use the BI system effectively.
Project Business Case