## Business Case
Project Information
Project Name | Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules. |  | Group | 4
Project Description | A Business Intelligence (BI) system for Golden Gate Restaurant Chain designed to centralize data, gain customer insights, optimize operations, enhance marketing effectiveness, and ensure scalability for long-term growth and adaptability.
Project Sponsor | Assoc. Prof. Ho Trung Thanh, Ph.D.
Program Manager | Assoc. Prof. Ho Trung Thanh, Ph.D.
Project Manager | To Nguyen Tuong Vy
Organization(s) | Golden Gate Restaurant Chain
Target Start Date | 3rd January, 2025 | Target End Date: | 11th March, 2025
Business Needs/Project Goals
- Centralize and unify data from all brands into a single data warehouse for streamlined analysis, reporting, and decision-making. - Gain insights into customer behavior and feedback to enhance personalized marketing, service quality, and customer satisfaction. - Optimize operational efficiency by tracking KPIs, improving forecasting, managing inventory, and reducing costs. - Measure marketing effectiveness and ensure the BI system is scalable to support Golden Gate’s growth and evolving needs.
Project Scope
In-scope |  |  | Out of scope
- Data integration and infrastructure. - System development and reporting. - Marketing and sales analysis. - User training and support. - Security and compliance. |  |  | - Third-Party campaign execution. - Customer-Facing platforms. - External consulting and maintenance beyond initial setup.
Constraints | - Time: 2 months. - Scope: Enabling data integration, real-time reporting, and insights to enhance customer understanding, optimize marketing, and improve operational efficiency while supporting scalable decision-making. - Budget: 1 Project Manager, 1 Business Analyst, 1 QA/QC, 1 Data Analyst, 1 Product Developer - Quality: The focus will be on delivering on time and within budget, with less emphasis on additional features or non-essential improvements.
Key Risks | - Limited resources (Time and Budget constraints). - Inconsistent or low-quality data. - Integration with legacy systems. - Misalignment of business requirements. - System usability issues. - Lack of thorough testing.
Assumptions | - The required data from restaurant operations, sales, and marketing will be available and accurate. - Necessary software and hardware resources for the BI system will be provided. - The team has the necessary skills in BI, data analytics, and restaurant industry processes. - There will be no major changes to the existing business processes during the project. - Stakeholders will provide timely feedback and approvals as needed.
Project Budgets | 1. Software and Licensing BI Tools (Power BI) – Enterprise licenses for centralized BI reporting: 0 ETL Tool Licensing (Visual Studio 2022) – Data pipeline automation: 20,000 Database License (SQL Server on-premises) – Data formatting and storage: 80,000 2. Evaluation and Requirement Gathering Surveys & Questionnaires – Collecting reporting needs and KPIs: 250 Process Documentation – Mapping workflows, identifying data sources: 300 Requirement Validation – Reviewing and refining requirements with stakeholders: 250 Competitive Benchmarking – Analyzing competitors’ BI solutions: 300 3. Data Integration and ETL (Extract, Transform, Load) Custom Development for ETL Pipelines – Connecting POS, CRM, ERP data: 7,000 API & Connector Development – Integrating BI with internal systems: 15,000 Data Cleaning & Quality Management – Ensuring data consistency and accuracy: 2,500 4. Data Analysis Descriptive Analytics – Generating summary reports on sales and inventory: 1,500 Predictive Analytics – Forecasting trends and optimizing operations: 2,000 Customer Insights Analysis – Understanding customer behavior and preferences: 1,500 5. Data Visualization Dashboard Development – Creating interactive BI dashboards: 5,000 Report Customization – Tailoring reports for executives, managers, and finance teams: 2,500 6. Labor Costs (Salary) Project Manager (1 person): 600 Data Analysts & Engineers (1 person): 400 QA/QC Specialist (1 person): 400 Developer (1 person): 500 Business Analyst (1 person): 500 7. Consulting Services BI Consulting Fees (External Experts) – Customization and expert support: 4,000 8. User Training Training Sessions for Employees (120 employees) – Online or in-person training: 3,000 Training Materials (Documentation, Videos, Guides) – Content creation costs: 1,500 9. Testing Functional Testing – Ensuring dashboards, reports, and integrations work correctly: 1,500 Performance Testing – Testing query speed and report load time: 1,500 Security & Compliance Testing – Ensuring data security and regulatory compliance: 1,500 User Acceptance Testing (UAT) – Final user testing before deployment: 1,500 10. Implementation Costs Internet & Network Expenses – Dedicated broadband for 20 locations: 1,800 Electricity & Power Costs – Energy consumption for servers and workstations: 2,200 Office Setup & Operational Costs – Temporary workspace for BI deployment team: 11,000 11. Maintenance and Support System Updates & Patches – Ongoing bug fixes and version upgrades: 1,000 Backup & Disaster Recovery – Cloud or on-prem backup solutions: 400 12. Cloud Infrastructure (AWS) Cloud Storage – Storing transaction and customer data: 1,000 BI Servers & Compute Instances – Running BI analytics and processing queries: 4,000 13. Networking Equipment Enterprise-Grade Firewalls – Securing data transmission across locations: 10,000 Redundant VPN Setup for Secure Remote Access – Secure access for executives and analysts: 1,200 Total Cost: $187,600
Project Team |  | Key Project Milestones
Name | Role | 1 | Finalize the official project plan, defining the scope, objectives, and timeline.
To Nguyen Tuong Vy | Project Manager | 2 | Gather and analyze business requirements, and identify key performance indicators (KPIs) for marketing and sales.
Nguyen Que Anh | Business Analyst | 3 | Develop the architecture and design of the BI system, ensuring it aligns with business needs.
Ngo Thanh Van | QA/QC | 4 | Allocate resources and assign tasks to development and testing teams.
Nguyen Huynh Kim Suong | Product Developer | 5 | Provide a demo version of the BI system to stakeholders after initial development.
Tran Thi Thuy Loi | Data Analyst | 6 | Conduct thorough system testing, ensuring functionality and data accuracy.
|  | 7 | Deliver the final, fully-tested product after addressing any issues from testing.
|  | 8 | Handover the product to the customer for review and collect feedback.
|  | 9 | Obtain customer approval and formally close the project.
Project Charter