## Sheet1
Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules - Project Scope Statement
Project Sponsor: Assoc. Prof. Ho Trung Thanh, Ph. D Project Manager: To Nguyen Tuong Vy Target Kick-Off Date: 3th January, 2025 Target Completion Date: 11th March 2025
Project Goal: - Implement business intelligence to streamline operations by centralizing data from POS, warehouse, and CRM systems for clear analysis. - Use SQL Server, Visual Studio, and MDX to manage and analyze databases, supporting sales and marketing. - Enable data-driven decisions with real-time insights using tools like Power BI, Tableau, and Excel for reports and forecasts. - Boost restaurant performance by optimizing operations across 15 branches and enhancing customer satisfaction through trend analysis and behavior insights. - Displaying KPIs such as revenue, profit margins, customer count, and expenses…
Scope Description: BI system will integrate data from various sources, including POS, warehouse management, and CRM systems, into a unified platform, ensuring real-time accuracy and consistency. By providing actionable insights, improve the operational efficiency of 15 branches, boost restaurant performance, and improve customer satisfaction.
Deliverables: - Official Project Plan: Goals and Scope - Centralized Data Platform - Interactive Dashboards - Customizable Reports - Trend Analysis and Forecasting - Marketing Analysis - Restaurant Performance Metrics
Challenges / Constraints: - Resource Limitations (Time and Budget): Break the project into phases to prioritize critical functionalities and ensure timely delivery. - Complex Data Integration and Standardization: Work closely with technical teams from each system to ensure compatibility and resolve integration issues promptly. - Data Security and Privacy Risks: Implement clear data access control, encryption, and security protocols in line with industry standards. - Inadequate User Adoption and Training: Collect user feedback on system usability and make necessary adjustments to improve the user experience. - Inadequate Testing and Quality Assurance: Repeat tests to increase testing efficiency and reduce error.
Acceptance criteria: - The delivered BI system must meet all defined objectives - All deliverables must be fully functional, thoroughly tested, and meet quality standards. - The system must address the needs and expectations of key stakeholders. - The project must be completed within the agreed timeframe and budget constraints. - Approver: Golden Gate’s Executive Sponsor for the project, typically a senior executive or representative from the management team overseeing the BI initiative.
Approver: Golden Gate’s Executive Sponsor, typically a senior executive or representative from the management team overseeing the BI initiative across 15 branches.
Assumptions: - All team members have the skills and knowledge needed to use tools like SQL Server, Visual Studio… to complete their tasks effectively. - Data from the POS, warehouse and CRM systems will be available and suitable for analysis and integration into the central data warehouse. - All necessary hardware and software will be accessible and sufficient to meet project needs. - Stakeholders will actively take part in gathering requirements, reviewing progress, and testing the system during User Acceptance Testing (UAT). - The project scope and requirements will stay consistent after the initial planning and requirement-gathering stages. - The allocated budget will be enough to support all project activities.