## Sheet1
Roles |  | Sponsor - Ho Trung Thanh | Project Manager - To Nguyen Tuong Vy | Business Analyst - Nguyen Que Anh | QA/QC - Ngo Thanh Van | Product Developer - Nguyen Huynh Kim Suong | Data Analyst and Engineer - Tran Thi Thuy Loi
Deliverables or Tasks |  | PMO |  | Production Department |  | Production Department
Project Management
| Appoint PM and support project | A |  |  | I | I |  | R | Responsible
| Project Planning and Kick-Off | C | A/R | C |  | C |  | A | Accountable
| Weekly Status Report | I | A/R | I | C | I |  | C | Consulted
Phase 1: Business requirement collection | [7 empty] | I | Informed
| Market Research |  | A | C | R
| Analysis report about customer (SWOT, Current Status, Business requirement,...) | I | A | R |  | I
Phase 2: Implementation
| Distribute resources based on each sprint or phase |  | R | I |  | C | I
| Build additional capacity / upgrades | I | A/R |  |  | I
| Evaluate product functionality at every stage | I |  |  | C |  | R
| Process report/meeting | I | A/R | I |  | I | I
Phase 3: Testing
| Comprehensive testing on the system is completed |  | A |  | C | I | R
| Testing report | I | A |  | R |  | I
RACI MATRIX
*Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules