## Activity List - Summary
ID | Activity list
0 | Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules
1 | Initiation and Planning
2 | Requirement Analysis
3 | Data Preparation and Modeling
4 | Data Integration
5 | Development of Marketing Module
6 | Development of Sales Module
7 | Testing and Quality Assurance
8 | Deployment and Training
9 | Post Implementation Review
10 | BI Solution Report Completion
11 | BI PROJECT CLOSURE AND COMPLETE
Activity List

## Activity List - Details
ID | Activity list
0 | Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules
1 | Initiation and Planning
1.1 | Introduction to Golden Gate Company
1.1.1 | Vietnam’s F&B Industry
1.1.2 | Golden Gate overview
1.1.3 | Golden Gate Major Milestones and Innovation
1.2 | Research the current status of the Golden Company
1.2.1 | SWOT Analysis
1.2.2 | Porter’s 5 forces analysis of Golden Gate Company
1.2.3 | Business Requirements/Problems
1.3 | Define Project Scope and Objectives
1.4 | Cost baseline analysis and budget estimate
1.4.1 | COCOMO analysis
1.4.2 | Payback and NPV analysis
1.4.3 | ROI analysis
1.4.4 | Break-Even analysis
1.5 | Define Project Business Case
1.6 | Define Project Charter and Assemble Project Team
1.7 | Define Project Development Lifecycle
1.8. | Initiation and Planning Complete
2 | Requirement Analysis
2.1 | Conduct detailed stakeholder interviews and surveys
2.2 | Analyze existing business processes to understand current workflows
2.3 | Identify key performance indicators (KPIs) needed for success
2.4 | Draft user stories and detailed use cases
2.5 | Review all identified requirements with stakeholders
2.6 | Revise and finalize the requirements documentation
2.7 | Secure stakeholder sign-off on the approved requirements
2.8 | Requirement Analysis Complete
3 | Data Preparation and Modeling
3.1 | Collect and review existing datasets from all relevant departments (Sales&Marketing)
3.2 | Perform data cleaning
3.2.1 | Identify and handle missing values
3.2.2 | Remove duplicate records
3.2.3 | Standardize data format
3.3 | Transform raw data into structured formats suitable for modeling
3.4 | Develop initial data models
3.4.1 | Create data schemas and relationships
3.4.2 | Define primary and foreign keys
3.4.3 | Bus Matrix
3.4.4 | Master Data
3.4.5 | Transactional Data
3.4.6 | Fact and Dimension Tables
3.4.7 | Relationships
3.5 | Validate the data models against the approved requirements
3.6 | Iterate on data models, incorporating stakeholder feedback
3.7 | Document the final data model design for reference
3.8 | Data Preparation and Modeling Complete
4 | Data Integration
4.1 | Analyze source systems to determine data extraction points
4.2 | Design ETL (Extract, Transform, Load) workflows
4.2.1 | Map source data fields to target data fields
4.2.2 | Define transformation rules and data cleansing steps
4.3 | Set up the data integration environment
4.4 | Conduct test runs of the ETL process with sample data
4.5 | Verify that integrated data meets accuracy and consistency standards
4.6 | Implement automated processes for regular data refreshes
4.7 | Document the entire integration process for future reference
4.8 | Data Integration complete
5 | Development of Sales Module
5.1 | Create sales performance dashboards
5.2 | Develop tools for sales trend analysis
5.3 | Implement regional and product-specific sales reporting
5.4 | Integrate POS (Point of Sale) data into reporting
5.5 | Development of Marketing Module Complete
6 | Development of Marketing Module
6.1 | Build campaign performance dashboards
6.2 | Implement customer segmentation analysis tools
6.3 | Develop social media and email marketing metrics tracking
6.4 | Integrate customer feedback analysis
6.5 | Development of Marketing Module Complete
7 | Testing and Quality Assurance
7.1 | Perform unit testing on individual components
7.2 | Conduct system integration testing
7.3 | Validate data accuracy and consistency
7.4 | Execute user acceptance testing (UAT)
7.5 | Testing and Quality Assurance Complete
8 | Deployment and Training
8.1 | Deploy BI system to production environment
8.2 | Provide training sessions for marketing and sales teams
8.3 | Develop user manuals and reference guides
8.4 | Offer ongoing support during the transition period
9 | Post Implementation Review
9.1 | Document all outcomes and lessons learned from the review
9.2 | Distribute to team members
9.3 | Create software maintenance team
9.4 | Address any issues identified during the post-implementation phase
9.5 | Post implementations review complete
10 | BI Solution Report Completion
10.1 | Collect and organize all project documents
10.2 | Perform content validation and quality checks
10.3 | Format the report
10.4 | Add visual documents
10.5 | Make presentation
11 | BI PROJECT CLOSURE AND COMPLETE
Activity List - Details