## Lessons Learned
LESSONS LEARNED
Today's Date: | 2025-01-03
Project Name: | Business Intelligence (BI) System for Golden Gate Restaurant Chain – Marketing and Sales Modules.
Project Manager: | To Nguyen Tuong Vy
WIN / ISSUE | Category | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
WIN | Design | Creating the Fact table is a critical and complex task. The team struggled with building it due to a lack of experience and reference materials. | The team faced delays building the Fact table but gained experience, improved data modeling, and enhanced problem-solving for future tasks. | Future projects will benefit from better training and documentation to ensure the team has the necessary expertise. Standardized guidelines and best practices can be developed to streamline the process and avoid similar challenges. | 1. Create a knowledge base with best practices for Fact table design. 2. Train the team on Fact table design and data modeling. 3. Assign mentors to support junior members.
ISSUE | Requirement Gathering | Golden Gate's fragmented data management system causes inefficiencies, as different brands use different POS, CRM, and inventory systems, making data consolidation difficult. | The fragmented data system causes inefficiencies, reporting delays, and analysis inconsistencies, making decision-making harder and hindering operational performance due to the lack of a unified view across brands. | Standardize POS, CRM, and inventory systems across all brands for better efficiency. Prioritize early integration planning to avoid inconsistencies. | 1. Standardize POS, CRM, and inventory systems across all brands. 2. Implement a centralized data management strategy to streamline integration. 3. Establish cross-brand data governance policies to ensure consistency.
WIN | Deploy | During implementation, the team discovered several data errors and inconsistencies across different software versions. | Finding data errors early helped avoid reporting and decision issues. The team fixed mistakes, improved data quality, and made the system more reliable. | Adopt proactive data validation early. Use automated checks to detect issues before they affect operations. | 1. Use automated data validation before and during implementation. 2. Set up a dedicated data quality assurance process. 3. Perform regular system audits to detect and fix inconsistencies early.
WIN | User Acceptance Testing | Employees struggled to adapt to the new BI system due to unfamiliarity with data analytics tools and resistance to change. Many found the interface complex and had difficulty extracting insights. | User resistance and lack of familiarity with analytics tools slowed down adoption, reducing the initial effectiveness of the BI system. Training programs were needed to improve user competency. | Future projects need a structured change management process to document scope changes and plan budget adjustments. Clear client communication on cost impacts is also essential. | 1. Establish a clear change request process with cost analysis. 2. Allocate contingency budgets for unexpected changes. 3. Communicate proactively with clients to manage expectations.
WIN | User Acceptance Testing | Changes in client requirements during the project implementation may result in an increased budget. | Changes in client requirements increased the budget, enabling better features, functionality, and business alignment. This flexibility led to a more tailored and effective solution. | Using advanced analytics and attribution models can improve ROI measurement. Controlled testing and AI insights help remove external factors for better campaign evaluation. | 1. Use advanced analytics to track marketing ROI accurately. 2. Create a standardized framework to measure campaign effectiveness. 3. Apply A/B testing to isolate promotion-driven revenue changes.
ISSUE | Testing | Difficulty in evaluating the ROI of marketing campaigns due to external factors, making it hard to assess promotion-driven revenue increases. | Difficulty in measuring ROI made it harder to optimize marketing spend and assess campaigns. Lack of clear insights weakened data-driven decisions, risking poor budget use and missed revenue growth. | Standardizing software versions across all team members will be a priority in future projects. A centralized software update policy should be enforced to avoid compatibility issues and ensure smooth collaboration. | 1. Standardize software versions across the team. 2. Use centralized version control for consistency. 3. Train regularly on software updates.
ISSUE | Coding and Unit Testing | There were inconsistencies in the versions of SQL Server, Power BI, and Visual Studio used by different team members. | Software version mismatches caused delays, errors, and collaboration issues, requiring extra time for standardization. | Future projects will enforce strict data governance with uniform security policies. Regular audits and compliance checks will reduce integration risks. | 1. Establish strict data security policies across all brands. 2. Conduct regular security audits and compliance checks. 3. Provide cybersecurity training to all relevant stakeholders.
ISSUE | Design | Data security issues arose due to inconsistent governance across brands, leading to potential risks during integration. | Inconsistent governance increased data breach risks, compliance issues, and integration failures, requiring stronger security and standardized policies. | A more thorough assessment of legacy systems should be conducted before implementation. Future projects should allocate more time for integration planning and consider middleware solutions earlier to reduce delays. | 1. Assess legacy systems before integration. 2. Preemptively implement middleware to bridge gaps. 3. Allow extra time for integration challenges.
WIN | Deploy | The team encountered difficulties integrating legacy systems with the new BI platform. These issues caused delays and required additional middleware solutions to bridge system gaps​. | Despite early challenges, the team implemented middleware to connect systems, ensuring smooth integration between old and new platforms. This improved data flow, system compatibility, and future scalability. | A stronger change management policy will be enforced to track and evaluate scope changes. Future projects will include contingency budgets and predefined approval processes to manage financial impacts effectively. | 1. Implement change management with financial impact analysis. 2. Define clear scope control and approval guidelines. 3. Maintain a flexible contingency budget for adjustments.
WIN | Project Management | Budget overruns occurred due to new requirements and weak change management, leading to extra costs and resource reallocation. | Despite budget overruns, fund reallocation met changing needs, highlighting the need for better change management and financial planning. | Future projects should use A/B testing and multi-touch attribution to isolate promotion effects. Data teams must work closely with marketing to improve evaluation methods. | 1. Implement multi-touch attribution models for accurate ROI tracking. 2. Introduce AI-driven analytics to analyze the impact of external factors. 3. Enhance collaboration between marketing and data teams to refine evaluation methods.

## LOV
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN / ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve
Category: | Requirement Gathering
Design
Coding and Unit Testing
Deploy
Testing
User Acceptance Testing
Project Management
Others